## Sheet1
Category | Title | Description | Impact Status | Impact to Project | Potential Mitigation / Learning | JLTi
Group | Staging Environment Conflict | There is only one staging environment on the Group Sitecore instance and there was some pressure from Group to get our website out of the staging environment as to not affect the Group project work that was in progress. We were not aware of the fact that there was only one staging environment. | High | No impact as Group were able to continue without being effected by our presence in the environment however it raises the risk of how we would handle this if a real conflict did occur. | Scheduling and communication is important however having more than one environment would certainty mitigate this. | Since we have sitecore license limitations/stage environment is sharable across all the sites. So the impact might be raised by group team. This can be mitigated in two ways. 1. Group Project and Australia project PM's create the integrated project plan in the aspects of deployment timelines without conflicts. 2. Revist the sitecore licensing model (consumption based) and introduce the seperate environment for AU sites.
Group | Group Deployment / CAB Process | The Group deployment / CAB process was not well communicated. Only when we requested JLTi to schedule the production deployment were we made aware of the Group deployment process and the fact that someone needed to front up to the CAB meeting to present this request. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | As we understand this BSA site integration with group sites should be known in the beginning itself. If so there should be a discussion with group PM to understand the group project process and integration task. Going forward if we include the group project integration plan which covers the development practise, code review, testing activities like integration, regression, PEN, performance testing and deployment with RACI and timelines.
Group | Acceptance into Service | We were only made aware late in the project that we needed to go through the Acceptance into Services process. It was then communicated that Australia was out of scope of this but then later that decision was reversed so it needed to be done on very short notice. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | ??
Group | Penetration Testing | We were only made aware late in the project that we needed to undertake a penetration test on this website prior to go live. The UAT site was on boarded onto Whitehat for this purpose. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | In general every websites/application, undergo the PEN test before go-live in the security aspects. This may get tailored based on the project. Going forward this needs to be discussed/reviewed with Group/security Architect and include in the project/integration plan scope. Additionally If any AU specific security guideline also may be considered. Also Security Group architect can provide the application web security check-list to adhere/review before PEN test.
Group | Front End Code Review | We were only made aware late in the piece that a front end code review was required by Group. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | This code review process is in-place as the source code is common for Group sites and BSA. Since the code is developed by vendor and they mayn't be aware of impacts while making the changes in the existing code. Also after deployment the application support resides with JLT (not vendor). So code review is very important practise before accepting the code from vendor. Going forward this need be enforced as process and included in the project plan.
Group | Regression Testing | We were only made aware late in the piece that a regression testing was required by Group. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | This is again missing of integration plan. If we have that in-place we should be able to handle better.
Group | Performance / Capacity Testing | We were only made aware late in the piece that a performance / capacity testing was required by Group. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | Same as above
Group | UK Processes | UK processes and requirements were not well communicated or published. | High | Scrambling at the last minute to meet Group requirements. | Not required now that we are aware of the process however no formal documentation has been provided on these requirements and that would be very useful going forward. | This concerns can be addressed in two ways 1. Project kick-off meeting and discussion with Group PM/architect 2. Publish or Review Group Project Process in internal Wiki?
Group | Late Engagement of Solution Specialist | We were only made aware late in the piece that a Group Solution Specialist was required to provide "sign off" on our project prior to go live. | Medium | Scrambling at the last minute to meet Group requirements. | Document / understand requirements from Group, build into the project schedule going forward. | ??
Group | Reliance on Ensono | There was some cookie issues encountered that required the external vendor Ensono to resolve. | Medium | It took a couple of days to resolve this waiting for Ensono. | Not sure how this could be mitigated in the future, just acknowledgement of this reliance and getting a better understanding of what Ensono may be needed for. | Vendor not communicated to JLTi that BSA new code changes using the new cookie. It took some time to identify the issue and communicated ensono to whitelist the cookies from security aspects. As we understand this BSA application integration and deployment not known/communicated to infra. architect and ensono (vendor). Still JLTi and Infra architect supported during vacation to fast track and troubleshoot this issue in the production. As part of integration deployment plan if we include deployment support/ownership from group/ensono team, we get the people in-place well advance.
Group | Licence Assignment by Service Desk Team | This was a slow and painful process. Often there would be no response even after multiple follow up's. | Low | No impact. | Understand lead times required to ensure no schedule impacts. | This is again lack of integration or deployment plan. If we have the deployment plan in-place this will be covered
Group | Network connectivity issues | The Sitecore staging environment requires either a direct connection out of the firewall, or for Network Services to update the local host file on the proxy server. | Medium | Resources from Network Services required. Delay in testing resulted. | Schedule time with Network Services in advance. Additional cost for Sitecore sites due to Network Services resources being required. | This is infrastructure access is security requirement, all the servers is not accessible/across across all the regional IT location and vendor. This environmnet access has to be part of Project Initiation activities. Which includes Development tools purchase/access, connectivity establishment, environment access and development practise kt and etc..
Group | Lack of access to log files | Developers needed to go through JLTi to access log files when attempting to diagnose defects. This made debugging UAT bugs very time-consuming. | High | Impact to developer productivity. Increased cost compared to non-Sitecore websites | Development for the Sitecore platform is more expensive than developing out of Sitecore. | This delay is not due to log access. Sravani reviewed the code and there is no log enabled for troubleshooting. After that JLTi requested vendor to include troubleshooting log and code deployed to UAT for troubleshooting. Addtionally UAT environment and log access in restricted as a infra security requirement. This is applicable irrespective of sitecore/non-sitecore applications for everyone. In the JLTi perspective we have provided the UAT log as soon its being requested as this critical input for troubleshooting. Sitecore development cost is not expensive compare with other tools/application for the Web CMS features used in BSA sites. We have such flexibility in web CMS compare with other options and development team should understand and implement properly.
Group/JLTi | Project design | Developers were bound to the exsiting Sitecore project design and were unable to make any architectural changes or use new features. | Medium | New Sitecore features couldn't be used | Use Sitecore Helix feature to create Independent project solutions and to make existing Sitecore solutions more maintainable, reusable and convenient. | This helix principles introduced in 2016-Jan to support the Sitecore MVC architecture styles. This sitecore application being developed using sitecore 7.2 in 2014. During this time Sitecore webforms and component architecture supported in sitecore 7.2. Since then no architectural changes/migration implemented. This is one of the mandatory application architecture changes/upgrade required. Sitecore also reviewed and advised to to upgrade to Helix principles
JLTA | Specification Challenges | Systems Analyst wasn't an expert in writing technical specifications for Sitecore development / an external development vendor and this may have lead to some re-work. | Medium | Rework / changes requested. | Build up this knowledge to ensure specifications can tailored for a Sitecore implementation. | ??
JLTA | Admin Module Design Issue | The PRC admin module was design to be included as part of the "admin role", unknown to Australia that the admin role was only offered a very limited group as it gave access to all JLT Group sites on Sitecore. There was rework involved in shifting this module out of the admin role into a new role. | Medium | Rework / changes requested. | Build up this knowledge to ensure specifications can tailored for a Sitecore implementation.
JLTA | Design Resource | There was a new design resource on boarded and this was their first assignment. Then this resource left and there was no design resource avaliable. | Medium | Rework / changes requested. | Not required.
JLTi | Support Resource in JLTi | There was a very clear scope initially of what the roles / responsibility of JLTi and HTC was in the project however when Reddy left, our authority on standards / guidelines also disappeared. Sravani was the only Sitecore resource for a few months and all deployment activities were controlled by her. As we got close to the production deployment, the need for her time was important however because she had conflicting priorities, she was not able to dedicate the right level of support this project. | High | All activities that were dependent on JLTi may not have been dealt with in the most timely manner. | A Sitecore developer from the Australia team (Neha) was provided as a full time backfill resource however this didn't appear to mitigate the issue. Ensure that the resource allocation is agreed upfront and monitored as such, keep communications lines open with Group around potential impacts.
JLTi | Development Resource Access Restriction for Troubleshooting | The HTC developers weren't given admin access because of the risk associated with it so there was a big dependency on JLTi. This ties into the support resource item above. | Medium | All activities that were dependent on JLTi may not have been dealt with in the most timely manner. | Work out the best approach to ensure the external developers are equip with the right access to troubleshoot or ensure appropriate resource is avaliable to support this activity.
JLTi | JLTi management | Developers on this project expressed concerns with the way they were being managed by JLTi. | High
Sitecore | Large downloads | Sitecore requires the download of large database files. These files are so large (10s of gigabytes) that with the speed of the Internet connection in Australia, our downloads would often timeout and would have to be restarted. The files are so large that we do not have room on our F drive for them. All up, they took several days to be downloaded. | Low | Delay in developers commencing work. | Development for the Sitecore platform is more expensive than developing out of Sitecore.
Sitecore | Syncing of databases and configuration files | Sitecore requires large databases and configuration files to be synchronised between developers. We do not seem to have a good way of doing this. Tools are available to help automate but they're very expensive. | High | Impact to developer productivity. Increased cost compared to non-Sitecore websites | Development for the Sitecore platform is more expensive than developing out of Sitecore.
Sitecore | Difficulty reproducing bugs locally | Developers experienced different behaviour on their local PC to what was observed in the staging environment. This is partly why so many bugs were raised, but worse still make bug resolution very difficult. If developers cannot reliabily reproduce defects then fixing them is incredibly challenging. | High | Impact to developer productivity. Increased cost compared to non-Sitecore websites | Development for the Sitecore platform is more expensive than developing out of Sitecore.
Sitecore | Single bin folder | Sitecore treats all websites as a single, massive site. It is not possible to deploy one site without deploying all others. A change to a single website can therefore affect any other website. This is far from best practice but is unfortunately a limitation of Sitecore itself. | High | Higher cost due to development needs to consider total impact of change and regression testing being required. | Development for the Sitecore platform is more expensive than developing out of Sitecore. Risks of production issues is much higher.
Sitecore | Developer resources | It is hard to find developers with Sitecore experience. None of the developers from HTC were in Mumbai which meant they needed to travel to the JLT office. | High | Increased cost compared to non-Sitecore websites.
Sitecore | Developer training | Sitecore documentation is not available to developers without being certified. Certification is an expensive process. | Medium
Sitecore | Developer training | Sitecore development has a steep learning curve. The common view is that it takes 6 months of experience to become an proficient Sitecore developer. | High | Solution implementation may not be optimal and may not be easily corrected.
Sitecore | Lack of Community Support | There is a local Sitecore User Group, but only had 2 meetings in the last year. | Low
Sitecore/Group | Development Environment Setup | The intial setup time took much more time than expected because of Sitecore environment setup, group's exisitng code and database setup and provide access to all required environments and files. | Medium | Delayed start of actual development | This is a one time set-up issue for a developer's machine.
Vendor | HTC's Client Relationship Management | Client relationship management was poor. Unbeknownst to JLT, more effort was being expended on the project but only after the fact were we told that it's going to cost us more money. Also there have been occasions where HTC and JLT have not seen eye to eye on what constitutes a change request. | Medium | Additional cost however this was negotiated down to an acceptable level. | Agree more definitively what constitutes a change request. Agree that any change requests to the original estimate must be agreed up front rather than after the fact.
Vendor | Deployment Issues | Packages provided by the HTC developers were in some cases incomplete or wrong versions were provided which meant that Sravani spent more time on rework that she should of. Prabhu, when he joined provided some guidance to the HTC developers on this and since then it appears that this issue was not so prevalent. | Medium | Activities that should of been straight forward took more time due to rework. | Clear guidance on process and a checklist to ensure all accuracy and completeness of deployment packages.
Vendor | Quality of Development | The quality of the code developed by HTC was not the best and there was many bugs/issues found. | High | Multiple deployments to fix issues/bugs which ties into the JLTi resource issue. | Work out the best approach to ensure the external developers are equip with the right access / rights to test their code without any other resource being involved and implement the relevant code reviews to prevent this as much as possible.
Vendor | Resource Management Support from Vendor | When the resources returned to Bangalore, arguable there was less "control and visibility" of the resources. At the beginning of the project, we had Venkat (HTC) overseeing the resources and was the point of escalation however toward the end of the project, he was not very visible. | Medium | We didn't have as much visibility on progress, movements...etc. | Ideally have a "Manager" in place in the same office as the developer/s.
Vendor | Remote Office Arrangement | When the resources returned to Bangalore, there is no doubt that the arrangement was more challenging as we had no eyes/ears on the ground. | Medium | We didn't have as much visibility on progress, movements...etc. | Ideally have a "Manager" in place in the same office as the developer/s.
Vendor | Switching of Sitecore Developer Mid Project | Nilesh (original developer) was earmarked to start another project at the end of August so when the timelines for this project blew out, we were given no choice but to swap out Nilesh for another developer. | High | There was a significant amount of time spent by the new developer to get up to speed so there is no doubt we lost time / productivity as a result. | Have a minimum of two developers on our projects to ensure continuity and will reduce key man dependency.